## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Meghan | Sailor | Kevin | Julian | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 12 |  | 2
|  | Design architecture | Project Manager | Satterley, Meghan | 12 |  | 2 |  | 0 | 2 |  |  | 2
| Requirements |  |  |  |  | 9 |  | 12 |  |  |  |  | 0
|  | Gather | Project Manager | Satterley, Meghan | 2 |  | 4 |  | 1 | 1 | 1 | 1 | 4
|  | Analyze | Project Manager | Satterley, Meghan | 4 |  | 4 |  | 1 | 1 | 1 | 1 | 4
|  | Specify | Project Manager | Satterley, Meghan | 3 |  | 4 |  | 1 | 1 | 1 | 1 | 4
| Documentation |  |  |  |  | 28 |  | 26 |  |  |  |  | 0
|  | Project Charter | Project Manager | Satterley, Meghan | 2 |  | 3 |  | 0 | 3 |  |  | 3
|  | Release Plan | Project Manager | Satterley, Meghan | 2 |  | 3 |  | 3 | 0 |  |  | 3
|  | Requirements Document | Project Manager, Requirements Engineer | Usher, Sailor | 5 |  | 2 |  | 0 | 2 |  |  | 2
|  | Project Plan | Project Manager, Developers | Satterley, Meghan | 5 |  | 5 |  | 5 | 0 |  |  | 5
|  | Architecture Document | Architect | Usher, Sailor | 4 |  | 4 |  | 2 | 2 |  |  | 4
|  | Test Report | Tester | Usher, Sailor | 8 |  | 8 |  | 2 | 2 | 4 |  | 8
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Satterley, Meghan | 2 |  | 1 |  | 1 | 0 |  |  | 1
Front-end & Back-end
Iteration 1: | Development |  |  |  |  | 54 |  | 79 |  |  |  |  | 0
|  | Determine technology needs | Project Manager | Satterley, Meghan | 1 |  | 4 |  | 1 | 1 | 1 | 1 | 4
|  | Setup Development Environment | Developer | Membreno, Kevin | 20 |  | 19 |  | 4 |  | 15 |  | 19
|  | Implement user authentication | Developer | Membreno, Kevin | 8 |  | 8 |  |  |  | 8 |  | 8
|  | Design UI mockups | Developer | Davis, Julian | 5 |  | 8 |  | 3 |  |  | 5 | 8
|  | Implement HTML/CSS structure | Developer | Davis, Julian | 10 |  | 13 |  | 3 |  |  | 10 | 13
|  | Implement Multi-Factor Authentication | Developer | Membreno, Kevin | 8 |  | 8 |  |  |  | 8 |  | 8
|  | Set up PostgreSQL database | Developer | Membreno, Kevin, Satterley, Meghan | 2 |  | 19 |  | 8 |  | 8 | 3 | 19
| Analysis |  |  |  |  | 6 |  | 16 |  |  |  |  | 0
|  | System Testing | Tester | Membreno, Kevin | 2 |  | 4 |  | 2 |  |  | 2 | 4
|  | Bug fix as required | Tester, Developer | Membreno, Kevin, Satterley, Meghan, Davis, Julian | 2 |  | 8 |  | 2 | 2 | 2 | 2 | 8
|  | Evaluate needs for next iteration | Project Manager | Satterley, Meghan | 2 |  | 4 |  | 1 | 1 | 1 | 1 | 4
Integration and Testing
Iteration 2: | Design |  |  |  |  | 4 |  | 7 |  |  |  |  | 0
|  | Design Improvements | Developer | Satterley, Meghan | 2 |  | 3 |  | 2 |  |  | 1 | 3
|  | UI/UX Improvements | Developer | Satterley, Meghan | 2 |  | 4 |  | 2 |  | 1 | 1 | 4
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
| Development |  |  |  |  | 25 |  | 30 |  |  |  |  | 0
|  | Implement OpenAI Chatbot | Developer | Usher, Sailor | 4 |  | 6 |  |  | 4 | 2 |  | 6
|  | Implement Password Retrieval | Developer | Membreno, Kevin | 5 |  | 5 |  |  |  | 5 |  | 5
|  | Security Enhancements | Developer | Membreno, Kevin | 10 |  | 13 |  | 3 |  | 10 |  | 13
|  | Conduct unit testing | Developer | Membreno, Kevin | 4 |  | 4 |  | 2 |  | 2 |  | 4
|  | Integrate front-end and back-end components | Developer | Membreno, Kevin | 2 |  | 2 |  |  |  | 2 |  | 2
| Analysis |  |  |  |  | 6 |  | 17 |  |  |  |  | 0
|  | System Testing | Tester | Membreno, Kevin, Satterley, Meghan | 2 |  | 7 |  | 1 | 3 | 3 |  | 7
|  | Bug fix as required | Tester, Developer | Membreno, Kevin, Satterley, Meghan | 2 |  | 6 |  | 2 | 2 | 2 |  | 6
|  | Evaluate needs for next iteration | Project Manager | Satterley, Meghan | 2 |  | 4 |  | 1 | 1 | 1 | 1 | 4
Deployment & Doc | [6 empty] | 0
Iteration 3: | Development |  |  |  |  | 4 |  | 20 |  |  |  |  | 0
|  | Prepare for deployment | Developer | Sailor, Usher | 2 |  | 16 |  | 4 | 4 | 4 | 4 | 16
|  | Risk analysis | Developer | Satterley, Meghan | 2 |  | 4 |  | 2 |  | 2 |  | 4
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
| Documentation |  |  |  |  | 11 |  | 12 |  |  |  |  | 0
|  | Finalize project documentation | Developer | Satterley, Meghan, Usher, Sailor, Davis, Julian | 1 |  | 10 |  | 2 | 5 | 1 | 2 | 10
|  | Document user guides and manuals | Developer | Satterley, Meghan | 10 |  | 2 |  | 2 |  |  |  | 2
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
| Analysis |  |  |  |  | 5 |  | 24 |  |  |  |  | 0
|  | Acceptance Testing | Tester, Project Manager | Membreno, Kevin | 3 |  | 11 |  | 3 |  | 8 |  | 11
|  | Bug fix as required | Tester, Developer | Membreno, Kevin, Satterley, Meghan, | 2 |  | 13 |  | 3 | 2 | 8 |  | 13
Total |  |  |  |  | 164 | 164 | 245 | 245 | 69 | 39 | 101 | 36 | 245